## Start Here
hona
THE FIX & FLIP WORKBOOK
Run a flip without having run one before.
Answer the questions on Your Deal. Put six sold houses on Comps. Untick what this house does not need on Scope & Phases. Send the Bid Request to subs and type back what they quote. Everything else fills itself in.
WHERE YOU ARE
| Step | What it is | Done
| 1. Your Deal | Fourteen questions about the house, the money and your terms. | 14 | 14
| 2. Comps & Buy Box | Three sold as-is, three sold renovated. Gives you your ceiling. | 6 | 6
| 3. Scope & Phases | Untick anything this house does not need. | 52 | jobs
| 4. Bid Comparison | What each sub quoted — price and days. | 52 | priced
WHAT IT TELLS YOU
| Most you should pay |  | 276826.1431
| Rehab budget from your bids |  | 129325
| Cost per square foot |  | 69.5296
| Days on site |  | 155
| Extra cash you need between draws |  | 0
Blue cells are yours to fill in. Grey cells calculate themselves — leave them alone.
Need help? Email support@honafinancial.com with any question about this workbook.
When the numbers are right, the last sheet hands your project straight to Hona — and every receipt you scan lands against them. honafinancial.com

## Your Deal
Your Deal
Answer these in order. Everything else in this workbook fills itself in.
THE PROPERTY
1. Property address | 1421 E Cloud Rd, Queen Creek AZ
Street, city, state
2. Square footage | 1860
Heated and cooled area only
3. What are you paying for it? | 255000
Purchase price. Leave blank if you have not offered yet.
4. How rough is it? | Medium
Light / Medium / Heavy / Rebuild — this pre-ticks your scope
THE MONEY
5. How much are you borrowing? | 310000
Total loan amount including rehab draws
6. Interest rate | 11.5%
Annual rate, e.g. 11.5%
7. Points | 2
Origination points charged at closing
8. Days from draw request until your lender funds | 10
Ask them. This drives how much cash you carry.
9. How much of your own cash can you put in? | 60000
Cash available for deposits and carry, not the down payment
YOUR TERMS
10. When do you start? | 2026-10-19
First day of work on site
11. What do subs get up front? | 50%
Arizona residential standard is 50% down, 50% on completion
12. Does your lender hold back a retainage? | 10%
Percentage held from each draw until completion
13. Selling costs when you exit | 8%
Agent commission plus closing. 8% is a common default.
14. What profit are you aiming for? | 55000
Your number, not a formula. This sets your maximum offer.
Everything above is filled in with an example deal so you can see how it works. Replace it with yours.
Need help? Email support@honafinancial.com with any question about this workbook.

## Comps & Buy Box
Comps & Buy Box
Six sales tell you what this house is worth now, what it is worth finished, and the most you should pay.
AS-IS COMPARABLES — WHAT HOUSES LIKE THIS SELL FOR BEFORE ANYONE TOUCHES THEM
Address | Sq ft | Sold price | $ / sq ft | Notes
1188 E Silver Creek Rd | 1795 | 262000 | 145.961 | Sold as-is, dated kitchen
22410 S 213th St | 1902 | 271000 | 142.4816 | Estate sale, original baths
1640 W Kingman Loop | 1748 | 249000 | 142.4485 | Investor purchase, roof issue
|  | Average $ / sq ft | 143.6304
FINISHED COMPARABLES — WHAT HOUSES LIKE THIS SELL FOR RENOVATED (YOUR ARV)
Address | Sq ft | Sold price | $ / sq ft | Notes
1355 E Cloud Rd | 1880 | 529000 | 281.383 | Full reno, quartz + LVP
22188 S 214th Way | 1815 | 512000 | 282.0937 | Updated 2025, new HVAC
1502 W Kingman Loop | 1930 | 545000 | 282.3834 | Reno + pool resurface
|  | Average $ / sq ft | 281.9534
THE BUY BOX — THE MOST YOU SHOULD PAY FOR THIS HOUSE
Walk a neighborhood, type a square footage above, and this tells you your ceiling before you make an offer.
Estimated as-is value |  |  | 267152.4905
Estimated ARV (finished value) |  |  | 524433.2386
Less selling costs |  |  | -41954.6591
Less rehab budget |  |  | -129325
Less loan carry and points |  |  | -21327.4365
Less your target profit |  |  | -55000
MAXIMUM YOU SHOULD PAY |  |  | 276826.1431
You are paying |  |  | 255000
Under / (over) your ceiling |  |  | 21826.1431
Green means the deal clears your profit target at these numbers. Red means it does not.

## Scope & Phases
Scope & Phases
Everything a flip can need is already listed. Untick what this house does not.
Pre-ticked for a medium-scope flip. Put an x to include a job, clear the cell to drop it. Budget and days fill in from your bids.
Ph | Phase | Category | Use? | Budget | Days
A | Pre-Construction & General Conditions | Permits & Plan Review | x | 1275 | 12 | A-1
A |  | Design & Drafting |  | 0 | 0
A |  | Feasibility & Inspections | x | 750 | 4 | A-2
A |  | Impact & Utility Connection Fees |  | 0 | 0
A |  | Insurance | x | 1675 | 0 | A-3
A |  | Utility Setup & Deposits | x | 400 | 0 | A-4
A |  | General Conditions & Supervision | x | 4225 | 0 | A-5
A |  | Contingency Reserve | x | 6600 | 0 | A-6
1 | Demolition, Foundation & Underground | Mobilization | x | 800 | 2 | 1-1
1 |  | Hazmat Abatement |  | 0 | 0
1 |  | Selective Demolition | x | 4750 | 6 | 1-2
1 |  | Excavation & Grading |  | 0 | 0
1 |  | Foundation & Slab |  | 0 | 0
1 |  | Underground Plumbing |  | 0 | 0
1 |  | Septic |  | 0 | 0
1 |  | Underground Electrical & Service |  | 0 | 0
1 |  | Pest & Soil Treatment | x | 450 | 1 | 1-3
2 | Framing, Roofing & Rough MEP | Framing Labor | x | 3350 | 6 | 2-1
2 |  | Framing Material | x | 2725 | 2 | 2-2
2 |  | Structural Steel & Beams |  | 0 | 0
2 |  | Roofing | x | 6950 | 4 | 2-3
2 |  | Windows & Exterior Doors | x | 5450 | 3 | 2-4
2 |  | Rough Plumbing | x | 3875 | 5 | 2-5
2 |  | Rough Electrical | x | 4300 | 6 | 2-6
2 |  | Rough HVAC | x | 5975 | 4 | 2-7
2 |  | Low Voltage Rough |  | 0 | 0
2 |  | Rough Inspections | x | 300 | 3 | 2-8
3 | Insulation, Drywall, Doors, Trim & Paint | Insulation | x | 1850 | 2 | 3-1
3 |  | Drywall | x | 5625 | 8 | 3-2
3 |  | Interior Doors | x | 2025 | 3 | 3-3
3 |  | Trim & Millwork | x | 2550 | 4 | 3-4
3 |  | Stairs & Railings |  | 0 | 0
3 |  | Interior Paint | x | 4050 | 5 | 3-5
4 | Cabinets & Countertops | Kitchen Cabinets | x | 6075 | 4 | 4-1
4 |  | Bath Vanities | x | 1625 | 2 | 4-2
4 |  | Laundry & Utility Cabinets | x | 675 | 1 | 4-3
4 |  | Closet Systems |  | 0 | 0
4 |  | Countertops | x | 3700 | 3 | 4-4
4 |  | Cabinet Hardware | x | 550 | 1 | 4-5
5 | Tile & Flooring | Floor Prep & Leveling | x | 925 | 2 | 5-1
5 |  | Floor Tile | x | 3000 | 4 | 5-2
5 |  | Shower & Tub Surround Tile | x | 2475 | 4 | 5-3
5 |  | Backsplash Tile | x | 1000 | 2 | 5-4
5 |  | LVP / Hardwood / Laminate | x | 5200 | 4 | 5-5
5 |  | Grout, Sealer & Trim Pieces | x | 450 | 1 | 5-6
6 | Exterior & Landscaping | Stucco / Siding | x | 2900 | 5 | 6-1
6 |  | Fascia, Soffit & Gutters | x | 1400 | 3 | 6-2
6 |  | Driveway, Walkway & Hardscape |  | 0 | 0
6 |  | Fencing & Gates | x | 2150 | 3 | 6-3
6 |  | Pool Repair & Resurface |  | 0 | 0
6 |  | Exterior Paint | x | 3250 | 4 | 6-4
6 |  | Exterior Lighting | x | 575 | 1 | 6-5
6 |  | Landscaping | x | 4225 | 6 | 6-6
7 | MEP Finishes, Glass & Appliances | Plumbing Trim | x | 1750 | 3 | 7-1
7 |  | Electrical Trim | x | 1550 | 3 | 7-2
7 |  | HVAC Start-up & Registers | x | 700 | 2 | 7-3
7 |  | Shower Glass & Mirrors | x | 1850 | 2 | 7-4
7 |  | Bath Accessories | x | 450 | 1 | 7-5
7 |  | Appliances | x | 4050 | 1 | 7-6
7 |  | Garage Door & Opener | x | 1325 | 1 | 7-7
7 |  | Life Safety & Final Inspections | x | 400 | 2 | 7-8
8 | Punch, Carpet & Final Clean | Punch List & Touch-up | x | 1400 | 4 | 8-1
8 |  | Carpet | x | 1925 | 2 | 8-2
8 |  | Final Clean | x | 625 | 2 | 8-3
8 |  | Staging | x | 2200 | 2 | 8-4
8 |  | Warranty & Callback Reserve | x | 975 | 0 | 8-5
|  | Jobs included | 52 | 129325

## Bid Request
Bid Request |  |  |  | A — Pre-Construction & General Conditions
Pick a phase, print this page, hand it to a sub. They fill in price and days. |  |  |  | 1 — Demolition, Foundation & Underground
2 — Framing, Roofing & Rough MEP
3 — Insulation, Drywall, Doors, Trim & Paint
4 — Cabinets & Countertops
Which phase are you sending out? | 2 — Framing, Roofing & Rough MEP | #VALUE! |  | 5 — Tile & Flooring
|  | Opens your mail app with the whole request written. Add their address and send. |  | 6 — Exterior & Landscaping
Property | 1421 E Cloud Rd, Queen Creek AZ |  |  | 7 — MEP Finishes, Glass & Appliances
Contractor / sub |  |  |  | 8 — Punch, Carpet & Final Clean
Date sent
Please return by
SCOPE OF WORK
Category | Describe the work (you fill this in) | Your price | Days
Framing Labor
Framing Material
Roofing
Windows & Exterior Doors
Rough Plumbing
Rough Electrical
Rough HVAC
Rough Inspections
| TOTAL BID | 0 | 0
TERMS
• Deposit at start of work: this project pays a deposit, with the balance due on completion.
• Days above are calendar days from the day you start, not working days.
• Price is for labor and materials unless you note otherwise in the description.
• A signed lien waiver is required with each payment.
Questions about this request? support@honafinancial.com

## Bid Comparison
Bid Comparison
Type in what each sub quoted. The cheapest is used unless you pick another.
One bid gets you a budget. Three gets you the truth. Days come from the sub, not from you — leave Days at 0 for anything that runs the whole job, like supervision, insurance or a reserve.
Ph | Category | Use? | Bid 1 — company | Bid 1 $ | Days | Bid 2 — company | Bid 2 $ | Days | Bid 3 — company | Bid 3 $ | Days | Pick | Chosen $ | Days | Chosen sub
A | Permits & Plan Review | x | City of Queen Creek | 1275 | 12 | [7 empty] | 1275 | 12 | City of Queen Creek
A | Design & Drafting | 0 | [10 empty] | 0 | 0 | 0
A | Feasibility & Inspections | x |  | 750 | 4 | [7 empty] | 750 | 4 | 0
A | Impact & Utility Connection Fees | 0 | [10 empty] | 0 | 0 | 0
A | Insurance | x | Hartford | 1675 | 0 | [7 empty] | 1675 | 0 | Hartford
A | Utility Setup & Deposits | x |  | 400 | 0 | [7 empty] | 400 | 0 | 0
A | General Conditions & Supervision | x |  | 4225 | 0 | [7 empty] | 4225 | 0 | 0
A | Contingency Reserve | x |  | 6600 | 0 | [7 empty] | 6600 | 0 | 0
1 | Mobilization | x |  | 800 | 2 | [7 empty] | 800 | 2 | 0
1 | Hazmat Abatement | 0 | [10 empty] | 0 | 0 | 0
1 | Selective Demolition | x | Demo Pros LLC | 4750 | 6 | [7 empty] | 4750 | 6 | Demo Pros LLC
1 | Excavation & Grading | 0 | [10 empty] | 0 | 0 | 0
1 | Foundation & Slab | 0 | [10 empty] | 0 | 0 | 0
1 | Underground Plumbing | 0 | [10 empty] | 0 | 0 | 0
1 | Septic | 0 | [10 empty] | 0 | 0 | 0
1 | Underground Electrical & Service | 0 | [10 empty] | 0 | 0 | 0
1 | Pest & Soil Treatment | x |  | 450 | 1 | [7 empty] | 450 | 1 | 0
2 | Framing Labor | x | Framing Done Right LLC | 3350 | 6 | [7 empty] | 3350 | 6 | Framing Done Right LLC
2 | Framing Material | x | 84 Lumber | 2725 | 2 | [7 empty] | 2725 | 2 | 84 Lumber
2 | Structural Steel & Beams | 0 | [10 empty] | 0 | 0 | 0
2 | Roofing | x | Sun Valley Roofing | 6950 | 4 | Desert Ridge Roofing | 7925 | 5 | AZ Peak Roofing | 7375 | 3 |  | 6950 | 4 | Sun Valley Roofing
2 | Windows & Exterior Doors | x | Arcadia Glass Co | 5450 | 3 | [7 empty] | 5450 | 3 | Arcadia Glass Co
2 | Rough Plumbing | x | Copperline Plumbing | 3875 | 5 | [7 empty] | 3875 | 5 | Copperline Plumbing
2 | Rough Electrical | x | Voltz Electric | 4300 | 6 | Mesa Sparks LLC | 4900 | 7 | Rincon Electrical | 4550 | 5 |  | 4300 | 6 | Voltz Electric
2 | Rough HVAC | x | Sonoran Air | 5975 | 4 | [7 empty] | 5975 | 4 | Sonoran Air
2 | Low Voltage Rough | 0 | [10 empty] | 0 | 0 | 0
2 | Rough Inspections | x |  | 300 | 3 | [7 empty] | 300 | 3 | 0
3 | Insulation | x | Valley Insulation | 1850 | 2 | [7 empty] | 1850 | 2 | Valley Insulation
3 | Drywall | x | Level 5 Drywall | 5625 | 8 | Smooth Wall Co | 6400 | 9 | Canyon Drywall | 5950 | 7 |  | 5625 | 8 | Level 5 Drywall
3 | Interior Doors | x |  | 2025 | 3 | [7 empty] | 2025 | 3 | 0
3 | Trim & Millwork | x |  | 2550 | 4 | [7 empty] | 2550 | 4 | 0
3 | Stairs & Railings | 0 | [10 empty] | 0 | 0 | 0
3 | Interior Paint | x | Brushworks AZ | 4050 | 5 | [7 empty] | 4050 | 5 | Brushworks AZ
4 | Kitchen Cabinets | x | Copper State Cabinets | 6075 | 4 | Mesa Cabinet Works | 6925 | 5 | Sundance Millwork | 6450 | 3 |  | 6075 | 4 | Copper State Cabinets
4 | Bath Vanities | x |  | 1625 | 2 | [7 empty] | 1625 | 2 | 0
4 | Laundry & Utility Cabinets | x |  | 675 | 1 | [7 empty] | 675 | 1 | 0
4 | Closet Systems | 0 | [10 empty] | 0 | 0 | 0
4 | Countertops | x | Stone Age Surfaces | 3700 | 3 | [7 empty] | 3700 | 3 | Stone Age Surfaces
4 | Cabinet Hardware | x |  | 550 | 1 | [7 empty] | 550 | 1 | 0
5 | Floor Prep & Leveling | x |  | 925 | 2 | [7 empty] | 925 | 2 | 0
5 | Floor Tile | x | Tile Team LLC | 3000 | 4 | [7 empty] | 3000 | 4 | Tile Team LLC
5 | Shower & Tub Surround Tile | x |  | 2475 | 4 | [7 empty] | 2475 | 4 | 0
5 | Backsplash Tile | x |  | 1000 | 2 | [7 empty] | 1000 | 2 | 0
5 | LVP / Hardwood / Laminate | x | Desert Floors | 5200 | 4 | Legacy Flooring | 5925 | 5 | Saguaro Surfaces | 5500 | 3 |  | 5200 | 4 | Desert Floors
5 | Grout, Sealer & Trim Pieces | x |  | 450 | 1 | [7 empty] | 450 | 1 | 0
6 | Stucco / Siding | x | Adobe Stucco Co | 2900 | 5 | [7 empty] | 2900 | 5 | Adobe Stucco Co
6 | Fascia, Soffit & Gutters | x |  | 1400 | 3 | [7 empty] | 1400 | 3 | 0
6 | Driveway, Walkway & Hardscape | 0 | [10 empty] | 0 | 0 | 0
6 | Fencing & Gates | x |  | 2150 | 3 | [7 empty] | 2150 | 3 | 0
6 | Pool Repair & Resurface | 0 | [10 empty] | 0 | 0 | 0
6 | Exterior Paint | x | Brushworks AZ | 3250 | 4 | Gilbert Painting | 3700 | 5 | Red Rock Coatings | 3450 | 3 |  | 3250 | 4 | Brushworks AZ
6 | Exterior Lighting | x |  | 575 | 1 | [7 empty] | 575 | 1 | 0
6 | Landscaping | x | Verde Landscape | 4225 | 6 | Cactus Creek Outdoor | 4825 | 7 | Ironwood Grounds | 4475 | 5 |  | 4225 | 6 | Verde Landscape
7 | Plumbing Trim | x |  | 1750 | 3 | [7 empty] | 1750 | 3 | 0
7 | Electrical Trim | x |  | 1550 | 3 | [7 empty] | 1550 | 3 | 0
7 | HVAC Start-up & Registers | x |  | 700 | 2 | [7 empty] | 700 | 2 | 0
7 | Shower Glass & Mirrors | x |  | 1850 | 2 | [7 empty] | 1850 | 2 | 0
7 | Bath Accessories | x |  | 450 | 1 | [7 empty] | 450 | 1 | 0
7 | Appliances | x | Spencer's TV & Appliance | 4050 | 1 | Best Buy | 4625 | 2 | Ferguson | 4300 | 1 |  | 4050 | 1 | Spencer's TV & Appliance
7 | Garage Door & Opener | x |  | 1325 | 1 | [7 empty] | 1325 | 1 | 0
7 | Life Safety & Final Inspections | x |  | 400 | 2 | [7 empty] | 400 | 2 | 0
8 | Punch List & Touch-up | x |  | 1400 | 4 | [7 empty] | 1400 | 4 | 0
8 | Carpet | x | Desert Floors | 1925 | 2 | [7 empty] | 1925 | 2 | Desert Floors
8 | Final Clean | x | Sparkle Crew | 625 | 2 | [7 empty] | 625 | 2 | Sparkle Crew
8 | Staging | x | Staged AZ | 2200 | 2 | [7 empty] | 2200 | 2 | Staged AZ
8 | Warranty & Callback Reserve | x |  | 975 | 0 | [7 empty] | 975 | 0 | 0

## Budget & Schedule
Budget & Schedule
Your bids, rolled up. Phases run one after another; jobs inside a phase run together.
Total rehab budget |  |  | 129325
Cost per square foot |  |  | 69.5296
Calendar days on site |  |  | 155
Months of carry |  |  | 5.092
Ph | Phase | Jobs | Budget | Days | Starts | Finishes
A | Pre-Construction & General Conditions | 6 | 14925 | 16 | 2026-10-19 | 2026-11-03
1 | Demolition, Foundation & Underground | 3 | 6000 | 9 | 2026-11-04 | 2026-11-12
2 | Framing, Roofing & Rough MEP | 8 | 32925 | 33 | 2026-11-13 | 2026-12-15
3 | Insulation, Drywall, Doors, Trim & Paint | 5 | 16100 | 22 | 2026-12-16 | 2027-01-06
4 | Cabinets & Countertops | 5 | 12625 | 11 | 2027-01-07 | 2027-01-17
5 | Tile & Flooring | 6 | 13050 | 17 | 2027-01-18 | 2027-02-03
6 | Exterior & Landscaping | 6 | 14500 | 22 | 2027-02-04 | 2027-02-25
7 | MEP Finishes, Glass & Appliances | 8 | 12075 | 15 | 2027-02-26 | 2027-03-12
8 | Punch, Carpet & Final Clean | 5 | 7125 | 10 | 2027-03-13 | 2027-03-22
| TOTAL | 52 | 129325 |  |  | 2027-03-22
A phase takes as long as its jobs added together. On a house this size one trade works at a time.
Days come from what each sub quoted on the Bid Comparison sheet — they are calendar days, not working days.
Formulas:
Starts = [Finishes, row above]+1
Finishes = IF([Days]=0,[Starts]-1,[Starts]+[Days]-1)
Finishes = MAX(G12:[Finishes, row above])

## Draw Schedule
Draw Schedule
One draw per phase. Request when the phase finishes; the money lands later.
The gap between 'Request on' and 'Funded on' is the number of days you told us your lender takes.
Draw | Phase | Phase budget | Holdback | You receive | Request on | Funded on
1 | Pre-Construction & General Conditions | 14925 | -1492.5 | 13432.5 | 2026-11-03 | 2026-11-13
2 | Demolition, Foundation & Underground | 6000 | -600 | 5400 | 2026-11-12 | 2026-11-22
3 | Framing, Roofing & Rough MEP | 32925 | -3292.5 | 29632.5 | 2026-12-15 | 2026-12-25
4 | Insulation, Drywall, Doors, Trim & Paint | 16100 | -1610 | 14490 | 2027-01-06 | 2027-01-16
5 | Cabinets & Countertops | 12625 | -1262.5 | 11362.5 | 2027-01-17 | 2027-01-27
6 | Tile & Flooring | 13050 | -1305 | 11745 | 2027-02-03 | 2027-02-13
7 | Exterior & Landscaping | 14500 | -1450 | 13050 | 2027-02-25 | 2027-03-07
8 | MEP Finishes, Glass & Appliances | 12075 | -1207.5 | 10867.5 | 2027-03-12 | 2027-03-22
9 | Punch, Carpet & Final Clean | 7125 | -712.5 | 6412.5 | 2027-03-22 | 2027-04-01
| TOTAL | 129325 | -12932.5 | 116392.5
Holdback is released at completion. Until then it is money you have spent and not been paid for.
Formulas:
Funded on = IF([Phase budget]=0,"",[Request on]+'Your Deal'!$D24)

## Cash & Float
Cash & Float
What this job costs you to carry between paying subs and getting funded.
You pay a deposit when a phase starts and the balance when it finishes. The draw arrives days after that.
Ph | Phase | Deposit out | Balance out | Draw in | On this date | Cash position
A | Pre-Construction & General Conditions | -7462.5 | -7462.5 | 13432.5 | 2026-11-03 | 45075
1 | Demolition, Foundation & Underground | -3000 | -3000 | 5400 | 2026-11-12 | 39075
2 | Framing, Roofing & Rough MEP | -16462.5 | -16462.5 | 29632.5 | 2026-12-15 | 24982.5
3 | Insulation, Drywall, Doors, Trim & Paint | -8050 | -8050 | 14490 | 2027-01-06 | 38515
4 | Cabinets & Countertops | -6312.5 | -6312.5 | 11362.5 | 2027-01-17 | 40380
5 | Tile & Flooring | -6525 | -6525 | 11745 | 2027-02-03 | 38692.5
6 | Exterior & Landscaping | -7250 | -7250 | 13050 | 2027-02-25 | 35937.5
7 | MEP Finishes, Glass & Appliances | -6037.5 | -6037.5 | 10867.5 | 2027-03-12 | 36912.5
8 | Punch, Carpet & Final Clean | -3562.5 | -3562.5 | 6412.5 | 2027-03-22 | 40655
| Lowest your cash ever gets |  |  |  | 24982.5
| Extra cash you need to survive it |  |  |  | 0
This is the number that catches people. A fully funded deal still needs cash on hand between draws.

## Take Into Hona
Take Into Hona
This is your project, ready to build in the app. Phase, category, budget, days.
Rows marked x are your project. Set them up once in Hona and every receipt you scan lands against these numbers.
Ph | Phase | Category | Use? | Budget | Days
A | Pre-Construction & General Conditions | Permits & Plan Review | x | 1275 | 12
A | 0 | Design & Drafting | 0 | 0 | 0
A | 0 | Feasibility & Inspections | x | 750 | 4
A | 0 | Impact & Utility Connection Fees | 0 | 0 | 0
A | 0 | Insurance | x | 1675 | 0
A | 0 | Utility Setup & Deposits | x | 400 | 0
A | 0 | General Conditions & Supervision | x | 4225 | 0
A | 0 | Contingency Reserve | x | 6600 | 0
1 | Demolition, Foundation & Underground | Mobilization | x | 800 | 2
1 | 0 | Hazmat Abatement | 0 | 0 | 0
1 | 0 | Selective Demolition | x | 4750 | 6
1 | 0 | Excavation & Grading | 0 | 0 | 0
1 | 0 | Foundation & Slab | 0 | 0 | 0
1 | 0 | Underground Plumbing | 0 | 0 | 0
1 | 0 | Septic | 0 | 0 | 0
1 | 0 | Underground Electrical & Service | 0 | 0 | 0
1 | 0 | Pest & Soil Treatment | x | 450 | 1
2 | Framing, Roofing & Rough MEP | Framing Labor | x | 3350 | 6
2 | 0 | Framing Material | x | 2725 | 2
2 | 0 | Structural Steel & Beams | 0 | 0 | 0
2 | 0 | Roofing | x | 6950 | 4
2 | 0 | Windows & Exterior Doors | x | 5450 | 3
2 | 0 | Rough Plumbing | x | 3875 | 5
2 | 0 | Rough Electrical | x | 4300 | 6
2 | 0 | Rough HVAC | x | 5975 | 4
2 | 0 | Low Voltage Rough | 0 | 0 | 0
2 | 0 | Rough Inspections | x | 300 | 3
3 | Insulation, Drywall, Doors, Trim & Paint | Insulation | x | 1850 | 2
3 | 0 | Drywall | x | 5625 | 8
3 | 0 | Interior Doors | x | 2025 | 3
3 | 0 | Trim & Millwork | x | 2550 | 4
3 | 0 | Stairs & Railings | 0 | 0 | 0
3 | 0 | Interior Paint | x | 4050 | 5
4 | Cabinets & Countertops | Kitchen Cabinets | x | 6075 | 4
4 | 0 | Bath Vanities | x | 1625 | 2
4 | 0 | Laundry & Utility Cabinets | x | 675 | 1
4 | 0 | Closet Systems | 0 | 0 | 0
4 | 0 | Countertops | x | 3700 | 3
4 | 0 | Cabinet Hardware | x | 550 | 1
5 | Tile & Flooring | Floor Prep & Leveling | x | 925 | 2
5 | 0 | Floor Tile | x | 3000 | 4
5 | 0 | Shower & Tub Surround Tile | x | 2475 | 4
5 | 0 | Backsplash Tile | x | 1000 | 2
5 | 0 | LVP / Hardwood / Laminate | x | 5200 | 4
5 | 0 | Grout, Sealer & Trim Pieces | x | 450 | 1
6 | Exterior & Landscaping | Stucco / Siding | x | 2900 | 5
6 | 0 | Fascia, Soffit & Gutters | x | 1400 | 3
6 | 0 | Driveway, Walkway & Hardscape | 0 | 0 | 0
6 | 0 | Fencing & Gates | x | 2150 | 3
6 | 0 | Pool Repair & Resurface | 0 | 0 | 0
6 | 0 | Exterior Paint | x | 3250 | 4
6 | 0 | Exterior Lighting | x | 575 | 1
6 | 0 | Landscaping | x | 4225 | 6
7 | MEP Finishes, Glass & Appliances | Plumbing Trim | x | 1750 | 3
7 | 0 | Electrical Trim | x | 1550 | 3
7 | 0 | HVAC Start-up & Registers | x | 700 | 2
7 | 0 | Shower Glass & Mirrors | x | 1850 | 2
7 | 0 | Bath Accessories | x | 450 | 1
7 | 0 | Appliances | x | 4050 | 1
7 | 0 | Garage Door & Opener | x | 1325 | 1
7 | 0 | Life Safety & Final Inspections | x | 400 | 2
8 | Punch, Carpet & Final Clean | Punch List & Touch-up | x | 1400 | 4
8 | 0 | Carpet | x | 1925 | 2
8 | 0 | Final Clean | x | 625 | 2
8 | 0 | Staging | x | 2200 | 2
8 | 0 | Warranty & Callback Reserve | x | 975 | 0
|  | Project total |  | 129325
hona · honafinancial.com